A Survey on the Characteristics of
Projects with Success in Delivering Client Benefits

Magne Jørgensen1

1: Simula Research Laboratory, P.O. Box 134, 1325 Lysaker, Norway, magnej@simula.no

Abstract

Context: A large waste of resources in software development projects currently results from being unable to produce client benefits.

Objective: The main objective is to better understand the characteristics of successful software projects and contribute to software projects that are more likely to produce the planned client benefits.

Method: We asked 63 Norwegian software professionals, representing both the client and the provider role, to report information about their last completed project. In a follow-up survey with 64 Norwegian software professionals, we addressed selected findings from the first survey.

Results: The analysis of the project information showed the following: i) The project management triangle criteria of being on time, on budget, and having the specified functionality are poor correlates of the essential success dimension client benefits. ii) Benefit management planning before the project started and benefit management activities during project execution were connected with success in delivering client benefits. iii) Fixed-price projects and projects in which the selection of providers had a strong focus on low price were less successful in delivering project benefits than other projects. iv) Agile projects were in general more successful than other projects, but agile projects without flexible scope to reflect changed user needs and learning, or without frequent delivery to the client, had less than average success in delivering client benefits.

Conclusions: The software projects that were successful in delivering client benefits differed from the less successful ones in several ways. In particular, they applied benefit management practices during project execution, they avoided fixed-price contracts, they had less focus on low price in the selection of providers, and they applied the core agile practices - frequent delivery to the client and scope flexibility.

Keywords: Software projects, project success factors, client benefits, survey

# 1. Introduction

The high investment in software-based products and services together with the frequent failures of software development projects [1-5] imply that even small improvements in process and product performance would amount to great savings. Better knowledge about the factors that separate successful and failed software projects, as well as the use of this knowledge to improve industry practices are essential to achieve such improvements.

The importance of improving software development performance has led to numerous surveys on failure factors of software projects [6-13]. One of the earliest surveys on software project failure, conducted in 1967 and reported in [14], found that lack of support from top management, lack of competent software professionals, changing technology, changing user requirements, and insufficient project management were key failure factors. Interestingly, the failure factors of the early surveys on software project failures, such as the survey in [14], appear to be very much the same as those reported in more recent surveys on software projects. The 2012 McKinsey-Oxford survey [15], for example, reports that unclear objectives, lack of business focus, shifting requirements, technical complexity, an unaligned team, lack of skill, unrealistic schedule and reactive planning are the failure factors of software projects. In spite of the 45-year separation, with ample opportunities to learn from experience, it seems that software projects fail for very much the same reasons as in the early days of software development.

Although we may have had information about why software projects fail for a while, the step from knowing why to knowing how to improve the situation is challenging. To accomplish this, we need to understand the practical actions likely to reduce the risk of failures. Unfortunately, the empirical research on actions likely to improve the rate of software project successes is much less comprehensive. This hampers the software industry’s opportunity to be evidence-based when adopting new software development methods and project management strategies [16, 17].

This paper aims to contribute to the body of empirical knowledge on the characteristics of successful software projects, that is, to examine which actions and contexts are connected with a higher likelihood of software project success. We emphasize action and context elements with the potential to guide future projects and improve the likelihood that a project is successful in delivering the expected client benefits. In particular, we address project size, benefit management, client competence and involvement, contract type and agile practices. There is, to our knowledge, only limited empirical evidence on how these elements affect the client benefits of software projects. In particular, there is a lack of evidence about which elements of benefit management and agile practices that, if any, are the key client benefit success factors.

There is much research on how project characteristics are connected with the traditional “project management triangle” of success - defining success as being on time, being on budget and having the specified functionality. Our results contribute to the body of knowledge by focusing on the success dimension typically neglected in software engineering surveys: client benefits. The importance of including this project success dimension in the analysis of characteristics of successful software projects is demonstrated by the low correlation of the client benefit success dimension with the other success dimensions found in our survey. The finding that a software project is on time, on budget and has the specified functionality is consequently far from a guarantee that the project is a success from the viewpoint of the client.

The remaining parts of the paper are organized as follows: Section 2 gives brief summaries of previous work on the topics addressed in the survey, Section 3 describes the design of the survey, Section 4 reports the results from the analysis of the collected data, Section 5 discusses the results, Section 6 discussed the limitations, and Section 7 concludes.

# 2. Previous work

Previous work on software projects reports widely different success and failure proportions. This is to a large extent a consequence of a difference in the definitions of project successes and failures. When using the narrow definition that a failed project is one that is “aborted” or “cancelled”, the proportion of failed projects is reported to be around 10% [4-6]. When including projects that are either cancelled or get a very low score on one or more performance criteria the proportion increases substantially. The survey in [6], in which a project was defined as failed if it got the score “poor” or “fair” on four out of the five performance criteria (user satisfaction, ability to meet budget targets, ability to meet schedule targets, product quality and staff productivity) found a failure rate of 26%. The analysis of the nearly eight hundred thousand small outsourcing projects reported in [18] gave that 14% were either cancelled or had a client rating of “poor” or worse. Defining as failure every project that does not deliver the specified functionality, is over budget or is not on time characterizes the majority of all software projects - typically 50-80% - as failures [19]. In any case, it is well documented that the software industry has a substantial proportion of software projects that are not fully successful.

Numerous empirical studies and reviews exist on factors believed to contribute to a software project’s success, see for example [20-26]. These studies typically point to perceived success factors related to collaboration with and competence of the client, team skills, change and scope management processes, management support, planning and budgeting. In spite of the high number of studies on this topic, there has not been much empirical work that focused on the characteristics of software projects successful in their main purpose, namely to benefit the client. It has long been pointed out that a software project’s success is to a large extent dependent on whether the project manages to deliver the expected benefit to the client [27]. Nevertheless, surveys of software projects still tend to focus on success understood as being on time, being on budget and having the specified functionality, see for example [28]. In addition, there is, to our knowledge, a lack of surveys and data analyses on the correlation between different success dimensions of software projects. Studies from other types of projects suggest that the correlations between the project outcome dimensions budget control, time control and functionality as specified, and the client benefit outcome dimensions client satisfaction and business benefits, are very low [29, 30]. This suggests that the software engineering studies with a focus on budget control, time control and delivered functionality cannot be used to say much about the degree of client benefits.

It is frequently reported that longer-lasting [31] and higher-cost [4] IT projects are less successful than shorter and smaller projects. The complexity and coordination needs of software projects typically increase with their length and size, which consequently increase the risk of project problems. Larger projects have, on the other hand, occasionally been reported to be subject to economies of scale, see for example, [32], and lower cost overruns, see for example, [33]. Possible reasons for the conflicting results of the effect of project size on success, when success is related to cost and time overruns, are discussed in [34]. A confounding factor of many cost and time overrun analyses is that when a project gets into trouble it also lasts longer and costs more. In other words, it difficult to separate the extent to which a larger and longer-lasting project experiences more time or cost overrun because it is large from the extent to which it becomes larger and longer-lasting because it experiences more time or cost failure. When measuring project size as the actual cost or duration we may consequently exaggerate the effect of project size on lack of success. If project size is measured as the budgeted cost, as in the current survey, or duration, we may, on the other hand, underestimate the effect of project size on success. As a consequence, the prior results of the relations between project size and success should be interpreted with great care.

IT project benefit management, or benefit realization management, may consist of the following steps (adapted from [35, 36]):

- Identification of alternative investments and completion of cost-benefit analysis, for example, through the creation of business cases including both quantifiable and non-quantifiable benefits.

- Communication of expected benefits (business objectives of the project) to all stakeholders.

- Plans for the realization of the benefits, with roles and responsibilities.

- Implementation of the benefit realization plan. This should include benefit management activities, such as prioritizing deliveries in accordance with the estimated benefit during project execution, but may also include activities after the project completion.

- Evaluation of the degree of benefits actually achieved.

Several studies suggest that the above benefit management process is connected with an increased likelihood of a project delivering the expected benefits for the client [35, 37]. The focus on benefit management in software project processes is, however, quite recent and there is a need for more research into which of the above steps that are essential to achieving project success.

Not only are the provider characteristics essential for project success. Client involvement and competence are also of great importance. The significance of client involvement is illustrated by the finding that there was a large difference in project success between those clients investing less than 20% of their budget in their own IT resources and those investing more than 20% [38, 39] in outsourced software projects.  The focus of the above referenced studies are on organizations going from in-house to outsourcing, but they nevertheless show that leaving limited IT competence in one’s own organization affects the risk of project failure. Han, Lee [40] reported that clients with high IT capability were believed to have outsourcing success at a rate about twice that of clients with low IT capability. The client’s IT capability score was in this case measured as a combination of capabilities in technology management, organizational relationship, and provider management. The binary logistic regression analysis in [18] found that client characteristics was as good predictor of project failure as the provider characteristics, suggesting that an incompetent client is as problematic as an incompetent provider.

Surveys of software projects typically report that between 40 and 70% of the projects use fixed-price contracts, with the remaining being per-hour (or “time and material”) contracts [41-43]. We have been unable to find studies that report success rates for other types of software development contracts, such as risk-sharing or agile contracts.

Agile practices have recently become the default software development method in many countries, see for example [44]. Agile practices may include, among other things, frequent deliveries to the client, flexible scope (embracing change), close interaction with the client (the product owner), and automated testing [45]. Despite its widespread use, there are few empirical studies on the effect of agile software development on different success dimensions, see [46] for a comprehensive review of the state of knowledge. Knowledge about the effect of individual agile elements is especially relevant given the variation in how agile is implemented in different organizations [47]. The limited research available suggests that iterative development, continuous integration and collective ownership [48], the presence of correct delivery strategy, close interaction with the client [49], proper practice of agile techniques, a high caliber team and team involvement [11], together with proper planning and team involvement [45] are the elements with the strongest positive effect on project success.

Because of the importance of not wasting large amounts of resources on failed software projects, it is not surprising that there have been numerous empirical studies and review papers on how to make software projects successful. We have, however, failed to find much work on characteristics and actions connected with client benefits. This is the main motivation for the data collection and analyses of this paper.

# 3. Survey design

## 3.1 Respondents and project population

The invited survey respondents were Norwegian software development clients and providers visiting a seminar on software project management in August 2014. The survey was designed to be answered online and to ensure anonymity of the respondents and their projects. The main results of the survey, based on the built-in analysis functionality of the survey tool Qualtrics, were presented at the end of the seminar. Ensuring the anonymity of the responses and providing the feedback of the main survey results at the seminar’s end were designed to increase the respondents’ motivation to give accurate and valid responses. The survey is only used for the purpose of this study.

All participants were asked to provide information about the characteristics and outcome of the last completed software project they had been involved in. The selection of the last project reduces the risk that the sample of projects is biased towards the most successful or the largest software projects, and is more likely to lead to a representative selection of the recent software projects of the participants. Alternative selection methods, such as one self-selected project or one failed and one successful project, would easily bias the results.

Our sample of respondents and projects was characterized by:

- Response rate of 79% (63 out of 80 invited participants provided information about their last project). Not all responses were 100% complete (i.e., some gave the answer “Don’t know” to one or more questions due to lack of knowledge of the requested characteristics of the reported project).

- Fifty-four percent of the respondents represented the client side and 46% the provider side.

- Of the surveyed projects, 42% of the clients were in the private sector and 58% in the public sector.

- Seventy-five percent of the projects developed a new software application, 17% extended an existing application, and 8% adapted or introduced an off-the-shelf application.

- Thirty-four percent of the projects had a budget of more than 10 million euros, 33% between 1 and 10 million euros, and the remaining 33% a budget of less than 1 million euros.

- The motivations for starting the projects were distributed as follows (more than one motivation was possible):

  - Modernization (replacing legacy software):		60%

  - Increasing work/service efficiency:			51%

  - Introducing new services or products:			35%

  - Required changes (e.g. induced by new regulations):	29%

  - Other motivation (merging of companies, safety, etc.):	6%

Our sample of respondents is a convenience sample; that is, we included those who participated in the project management seminar. This may have affected, for example, the observed proportion of large projects or the proportion of projects developing new applications. For the purpose of analysing the indicators of successful projects, as opposed to making claims about the software industry’s success rate, we believe that a convenience sample of projects is reasonable as long as we do not try to extrapolate the results to software project populations substantially different from the surveyed population.

## 3.2 Success dimensions

There are many dimensions of software project success. The traditional project management triangle covers being on time, being on budget and with the specified functionality [50]. Many surveys on project success cover only these three success dimensions, see for example the Standish Group’s annual surveys on software project success (www.standishgroup.com) and the survey reported in [4]. In our survey, we decided to include three additional dimensions that we believe are essential for evaluating the success and failure of software projects:

- Client benefits, that is, the degree to which the project delivers the expected benefits to the client. This is the success dimension that our survey focuses on.

- The technical quality of the delivered software, including reliability, maintainability, and other non-functional characteristics.

- The efficiency, or productivity, of the project work.

Our dimensions reflect the importance of including dimensions regarding both development success and implementation success [51].

The ordinal scale used in our survey for the responses for each of the success dimensions includes the following values: “Successful” – “Acceptable” – “Not very successful” – “Not at all successful”. In addition, the respondents could answer “Don’t know” or “Other (please specify)”. The “Don’t know” responses were not included in the analyses. We examined the “Other (please specify)” responses on an individual basis and decided upon whether or not to include them in one of the categories.

Clearly, a response is a respondent’s perception of a project’s success, not an objective measure of a project’s actual performance. In addition, our success scale does not allow for elaboration of the respondent’s meaning of for example “successful” compared to just “acceptable” client benefits. The main reason for not using more objective and precise response scales is that, for several of the success dimensions, no such project information would be available; for example, most projects do not have objective and precise measures of client benefit, technical quality and project efficiency. In addition, for the success dimensions that typically have more objective information available - for example, time control, budget control and functionality completeness - this information would frequently not tell us the degree to which the project was a success or a failure on that dimension. As an example, a cost overrun of 20% may in one high uncertainty context be acceptable, but in low uncertainty contexts indicate a budget control failure. Similarly, delivering only 90% of the specified functionality may be acceptable if the non-delivered functionality is not essential, otherwise it would indicate a failure. Expert judgment-based assessments of the degree of success may consequently have the advantage that the context is, to a larger extent, taken into consideration. A drawback is that different people in different roles or with different backgrounds may give varying answers about the same project. This subjectivity may introduce some noise to the analyses, so that some true relationships are not found, but is less likely to lead to observation of false relationships. Our assumption is that there will be an acceptable level of agreement between the respondents as to what constitutes project success and what is unacceptable project performance, so that the stakeholders’ perceptions of the degree of success reflect the actual success.

## 3.3 Information collection and research hypotheses

Besides collecting information about each project’s success in terms of the success dimensions described in Section 3.2, we collected information about the following project characteristics:

- Budget

- Processes used for benefit management

- Client competence and involvement

- Contract type

- Software development process elements, with a focus on agile practices

The questions with the corresponding response alternatives are included in Appendix 1. To ensure that the questions were correctly understood and meaningful, we conducted two rounds of piloting with feedback from software academics and professionals. After completion of the survey we conducted an informal walk-through with four randomly selected respondents about their interpretations of the questions and use of the scales. All questions were perceived to be meaningful to answer and to have proper response categories. As part of the survey, the participants could comment on how meaningful they found individual questions of the survey. The few comments we received confirmed that the questions were meaningful.

Most parts of our analyses are exploratory, that is, without hypotheses stated in advance and with the goal of better understanding of the characteristics of successful software projects. For these analyses, we just report the results without any statistical tests. In addition to the exploratory analyses we formulated three hypotheses related to project success in delivering client benefits based on our earlier research on software project failures [18]:

- H1: Projects with processes for benefit management succeed more often in delivering client benefits.

- H2: Projects with a competent (H2a) and/or involved (H2b) client succeed more often in delivering client benefits.

- H3: Projects using fixed-price contracts succeed less often in delivering client benefits.

The hypotheses will be statistically tested using Fisher’s exact test. This test was chosen because some of the proportions we compare are based on a rather small number of observations. We will, when appropriate, include more than one explanatory variable in the analysis of connections to examine possible interacting effects.

## 3.4 The follow-up survey

The analysis of the results from the survey gave two surprising results, one related to the lack of effect of project size and one related to the lack of effect of client involvement, which we wanted to better understand. For this purpose we conducted a brief follow-up survey in April 2015 with many of the same participants from the original survey. To get more project data, we asked the participants to include information about the two last projects they had been involved in and to include cancelled as well as completed projects. The inclusion of cancelled projects was there to better analyze the connection between project size and project failure. The follow-up survey included a more specific question about the type of client involvement and contribution than in the original survey. Appendix 2 includes the questions of the follow-up survey.

We received information about 107 projects from 64 software professionals in the follow-up survey, which had a response rate of 85% (64 out of 75 invited respondents). Similarly to the original survey, about half of the respondents were on the client side (52%) and on the provider side (48%). The project sizes were comparable to those of the original survey, with slightly more small projects.

The results from the follow-up survey are included in the relevant sections that report the results of the original survey, namely, the sections discussing project size (Section 4.2) and client competence and involvement (Section 4.4).

# 4. Survey results

## 4.1 Project success outcome

The outcomes of the projects with regard to the six success dimensions are described in Table 1. We merged the success categories “Not very successful” and “Not at all successful”, due to few responses in each category, and named the merged category “Unsuccessful”.

As described earlier, we asked for information about the last completed software project. This means that the survey does not include cancelled projects. The reported proportion of unsuccessful projects is consequently likely to have been higher, and the other proportions slightly lower, had all the started projects been included in the survey. The letter n denotes the number of valid project responses for a question.

Table 1: Project success per dimension

| Success dimension | Successful | Acceptable | Unsuccessful |
| --- | --- | --- | --- |
| Client benefits (n=56) | 36% | 59% | 5% |
| Functionality (n=58) | 35% | 55% | 10% |
| Technical quality (n=58) | 24% | 66% | 10% |
| Budget control (n=53) | 38% | 40% | 22% |
| Time control (n=55) | 33% | 40% | 30% |
| Work efficiency (n=54) | 19% | 57% | 24% |

An analysis of the combination of successful assessments for the same projects showed that about half of the projects (52%) managed to complete with at least acceptable success on all dimensions. On the other hand, this means that almost half (48%) of the projects were unsuccessful in at least one of the success dimensions. Not surprisingly, the more success dimensions we include in the definition of failed projects, the higher the rate of failed projects. With many success dimensions, a high threshold for claiming success, and the requirement that a project has to be successful on all dimensions, there would be very few successful IT projects. A comparison, or statement, about the proportion of failed projects, without including information about the included success dimensions and how success has been measured is consequently not very meaningful.

The proportions of successful projects in Table 1 are similar to those reported for US software projects by Nelson and Jansen [52] with respect to the success dimensions budget and time control. This corresponds to the finding that a project’s success on these two dimensions are rather stable across different contexts [53].

The three dimensions with the highest proportion of unsuccessful projects were budget control (cost overruns), time control (delayed deliveries), and work efficiency (project work conducted inefficiently). The dimension with the lowest proportion of unsuccessful project was client benefit, where fully 95% of the completed projects delivered at least acceptable levels of client benefits. If this ability to give satisfactory client benefits is representative of software projects, it gives a different picture of the software project performance than the media headlines of software failures and well-known surveys, such as the Chaos Report by the Standish Group. Two potential reasons for this difference in describing software project performance are the one-sided focus of cost overrun in evaluating success and the selection bias of many surveys [54, 55].

Table 2 displays the correlations between the success dimensions. To calculate the correlations we used the original success scale, coded as follows: 1=successful, 2=acceptable, 3=not very successful and 4=not successful at all. The use of correlation analysis assumes ratio or interval scale variables, while our success variables are just ordinal scale variables. Consequently, the correlations should only be used as rough indicators of the strength of the connection between the different success dimensions.

Table 2: Correlations between success dimensions

| Success dimension | Client benefit | Functionality | Technical quality | Budget control | Time control |
| --- | --- | --- | --- | --- | --- |
| Functionality | 0.60 |  |  |  |  |
| Technical quality | 0.56 | 0.35 |  |  |  |
| Budget control | 0.27 | 0.37 | 0.16 |  |  |
| Time control | 0.30 | 0.45 | 0.48 | 0.66 |  |
| Work efficiency | 0.44 | 0.40 | 0.40 | 0.53 | 0.83 |

In many contexts, the delivered benefit to the client may be the most important success dimension. As can be seen from Table 2, success on client benefits is not strongly correlated with budget control and time control, that is, it would be misleading to use budget or time overruns as indicators of a successful project in terms of client benefits. Client benefits are to a larger degree correlated with delivering the planned functionality and the technical quality of the system, but even here the correlation is far from perfect. The strongest correlation is between work efficiency and time control.

Table 3 displays the differences in success rates reported by project providers and clients.

Table 3: Project success and respondent role

| Success dimensions | Client respondents | Provider respondents |
| --- | --- | --- |
| Client benefit (n=56) | 29% | 38% |
| Functionality (n=58) | 29% | 38% |
| Technical quality (n=58) | 21% | 31% |
| Budget control (n=58) | 38% | 38% |
| Delivery on time (n=55) | 32% | 34% |
| Work efficiency (n=54) | 15% | 24% |

Table 3 shows that the respondents representing the providers were typically somewhat more positive regarding the project outcomes than respondents representing the clients. This result is similar to that found in the survey presented in [35]. It is not clear the extent to which an increase in positivity is a result of the role, differences in the actual projects the respondents had been involved in or just random variations in responses. The observation that the most objective success indicators - those related to budget and time control - were more similar than the other factors indicates that the role of the respondent had some impact on the evaluation of project success. That is, those in the role of provider may have had a more positive view on benefits, functionality, technical quality and work efficiency than their clients. We will nevertheless join the responses of the clients and providers in the following analyses. This is acceptable, we believe, given that our main purpose is to analyze relationships between project characteristics and success, not to analyze how successful software projects are.

Table 4 displays the differences in success rates reported for projects with public and private clients.

Table 4: Project success and client type

| Success dimensions | Public client | Private client |
| --- | --- | --- |
| Client benefit (n=56) | 39% | 34% |
| Functionality (n=58) | 30% | 41% |
| Technical quality (n=58) | 26% | 25% |
| Budget control (n=58) | 39% | 31% |
| Delivery on time (n=55) | 26% | 34% |
| Work efficiency (n=54) | 13% | 22% |

Table 4 suggests that there were only small differences in project success depending on whether the project had a public or a private client. This is different from the results of our 2004 survey conducted with supposedly similar types of Norwegian IT projects, in which those with public clients had substantially higher cost overruns [56], but similar to a New Zealand study from 2007 [1] in which there were no large differences. It may be that the governmental agencies have become more professional IT clients and more successful in their projects since 2004.

## 4.2 Project size

Table 5 displays the proportion of projects perceived as a “Successful”, namely, those with a success score better than “Acceptable”, for each of the success dimensions and three budget size categories. Twenty-one projects were categorized as small (< 1 million euros), 20 as medium (1–10 million euros), and 20 as large (>10 million euros). One project had a budget size unknown to the respondent.

Table 5: Project success and budget size

| Success dimension | Small (< 1 mill. euros) | Medium (1–10 mill. euros) | Large (> 20 mill. euros) |
| --- | --- | --- | --- |
| Benefit (n=56) | 31% | 47% | 35% |
| Functionality (n=58) | 29% | 47% | 35% |
| Technical quality (n=58) | 24% | 28% | 25% |
| Budget control (n=58) | 24% | 47% | 47% |
| Delivery on time (n=55) | 29% | 35% | 35% |
| Work efficiency (n=54) | 24% | 12% | 24% |

The results in Table 5 suggest that, for all of the success dimensions, the projects with the highest budgets had similarly or greater success than those with the lowest budgets. There were not sufficient data about failed projects to enable an analysis of whether larger projects fail more often based on the original survey.

To enable an analysis of the surprising connection between project size and project failure, where we did not find that large IT projects were less successful, we conducted a follow-up survey (see design in Section 3.4 and questions in Appendix 2). The follow-up survey included, as opposed to the original survey, cancelled projects. This we expected would give more data on project failures and enable an analysis of whether or not the largest projects had, as reported in most previous surveys, more failures than the smallest.

The follow-up survey gave results on the relation between project size and success similar to that observed in Table 5; the large projects had about the same or higher proportions of successes as the smallest ones. However, when looking at the projects that were either cancelled or failed to deliver the expected benefits (20 projects), we found that the largest projects (>10 million euros) were strongly over-represented. The proportion of unsuccessful projects regarding client benefits was 25% for the large, 7% for the medium, and 6% for the small projects. This suggests that the largest IT projects are indeed more likely to fail than the smaller ones, but when not failing or being cancelled, they may be about as successful in delivering client benefits as the smaller ones.

## 4.3 Benefit management

To assess the effect of benefit management practices on client benefit success and other success dimensions, we included five statements related to the presence of benefit management practices. The statements on which the respondents were to agree or disagree were as follows:

- B1: A good cost-benefit analysis of different alternatives was completed before the project started.

- B2: The expected benefits were clearly communicated to and understood by the project stakeholders.

- B3: There were good plans for how and when to realize the expected benefits.

- B4: There were good processes for prioritizing and managing activities during the project with focus on achieving the expected benefits.

- B5: There were good processes for evaluating (quantifying or formally assessing) the achieved benefits after the project was completed.

For each statement, the respondents were asked to select one of the response alternatives: “Fully agree”, “Agree more than disagree”, “Disagree more than agree”, “Fully disagree”, and “Don’t know”. We merged the first two categories to form the category “Agree” and the two last categories to form the category “Disagree” to avoid too few observations for meaningful analyses in each category.

Our hypothesis (H1) was that projects with processes for and a focus on benefit management succeeded more often than the other projects in delivering client benefits. The results are displayed in Table 6, where the variable “Increase in client benefit success rate” is the difference in proportion of successful projects for those with the response category “Agree” and those with the response category “Disagree”. In the forthcoming analyses, the increase in success rate is always measured as the percentage point difference. The p-values are based on Fisher’s exact two-tailed test on differences in proportions.

The increase in success rate should be interpreted with the overall success rate for client benefit (36%) in mind. An increase from, for example, 20% to 40% is an increase of 20 percentage points, but also shows a doubling (100% increase) in success rate.

Table 6: Project success and benefit management

| Client benefit management practices | Proportion of responses with “Agree” | Increase in client benefit success rate (percentage points) |
| --- | --- | --- |
| B1: Cost-benefit analysis (n=51) | 47% | 6% (p=0.8) |
| B2: Communication (n=56) | 57% | 22% (p=0.2) |
| B3: Planning (n=54) | 33% | 31% (p=0.03) |
| B4: Prioritizing and managing (n=55) | 53% | 34% (p=0.02) |
| B5: Formal evaluation (n=54) | 31% | 19% (p=0.2) |

As can be seen in Table 6, there are systematic increases (and for B3 and B4 also statistically significant increases, at p<0.05) in success rates when benefit management practices are included. It is only with respect to the cost–benefit analysis motivating the project (B1) – typically the development of business cases and return on investment analyses - where we found no large increase in success rate. This suggests that an up-front cost-benefit analysis itself is far from a guarantee of a successful project. It is the benefit management processes related to project execution, in particular (B3) and (B4), which separated successful and unsuccessful projects.

We examined the two statistically significant indicators of client benefits, namely, those related to questions B3 and B4, to ascertain the extent to which they were indicators of the other success dimensions as well. The increases in success rates for those responding “Agree” and “Disagree” to the other success dimensions are displayed in Table 7.

Table 7: Benefit planning (B3) and benefit management during the project execution (B4)

| Success dimensions | Increase in success rate (percentage points) due to presence of benefit planning (B3) | Increase in success rate (percentage points) due to presence of prioritization and benefit management during project execution (B4) |
| --- | --- | --- |
| Functionality | 4% (n=51) | 35% (n=53) |
| Technical quality | 49% (n=52) | 9% (n=52) |
| Budget control | 3% (n=47) | 35% (n=48) |
| Delivery on time | 7% (n=49) | 12% (n=50) |
| Work efficiency | 9% (n=48) | 12% (n=49) |

Table 7 shows that both the presence of a benefit plan (B3) and the presence of benefit management during the project execution (B4) were connected with increased success in all success dimensions. Although the increases in success rate on the other success dimensions were typically small, there were no signs of adverse effects – for example, that a focus on benefit management would decrease the focus on budget control or some other success dimension. Note the large increase in technical quality due to the presence of a benefit plan (B3), and the large increase in success related to functionality in accordance with plan and budget control due to the presence of benefit management practices during the project (B4). These three potentially interesting connections should be subject to further studies. While it is not surprising that the presence of delivery prioritization processes may lead to better functionality and budget control, the strong connection between benefit planning and technical quality is harder to explain.

## 4.4 Client competence and involvement

To examine the effect of client competence and involvement on project success, we included the following two questions in our questionnaire:

- C1: How much IT-competence did the client have within its own resources (internal IT-competence)?

  - The possible responses were “Very much”, “Much”, “Some”, “Little” and “Very little”.

  - To avoid too few responses in some of the categories we merged the categories “Very much” and “Much” to form the category “Competent client” and the categories “Some”, “Little” and “Very little” to form the category “Less competent client”.

- C2: What was the proportion of the total project effort completed by the client’s own staff?

  - The possible responses were “More than 40%”, “Between 20 and 40%”, “Less than 20%” and “Almost nothing or nothing”.

  - To avoid too few responses in some of the categories, we merged those with “More than 40%” and “Between 20 and 40%” to the group “High client involvement” and those with “Less than 20%” and “Almost nothing or nothing” as “Low client involvement”.

The hypotheses were that increased client competence (H2a) and more client involvement (H2b) would lead to an increase in success rate in delivering client benefits. Notice that we did not define competence or types of involvement, but left the interpretation of that to the respondents. This has, as we will see, impact on our ability to interpret the results.

Our analysis of the responses showed that there was only a small increase, 7% (n=56, p=0.6), in client benefit success rate for those in the category “Competent client” and a decrease in success rate, 3% (n=52, p=0.8), for those in the category “High client involvement”. Consequently, our data do not support the hypotheses H2a and H2b.

In an examination of the few projects assessed to be unsuccessful, however, we found that all of them had a “Less competent client” or a “Low client involvement”. Consequently, it may be the case that low client competence and involvement are meaningful indicators of increased risk of failures, a result similar to that reported by [18]. Discussing this result with some of the provider survey participants, we ascertained that they found incompetent and non-involved clients to be challenging, but also that high competence and involvement did not always lead to the type of contributions they needed from the client, which was more related to giving input about needs and priorities and making decisions without delaying the projects.

To analyze whether the effect of client attributes remained non-significant if we emphasized client contributions rather than client competence and involvement, we included a question on this in the follow-up survey. In this survey, we tried to be more explicit about the essential contribution of the client to the project, that is, the degree to which they perceived that they as clients (if the respondent was from the client side) or that the client (if the respondent was from the provider side) had been able to prioritize requirements, take decisions, and focus on business benefits. The response alternatives were “To a large degree”, “To some degree”, and “To a small or no degree”. There were few responses with “To a small or no degree” and we joined this category with the category “To some degree”. The responses, with valid data from 107 projects, are displayed in Table 8. The responses from clients and providers were, on average, very similar and are merged.

Table 8: Client benefit success and degree of client contribution in follow-up survey

| Client contribution | Successful | Acceptable | Unsuccessful |
| --- | --- | --- | --- |
| Large degree (n=41) | 66% | 34% | 0% |
| Some/small/no degree (n=66) | 14% | 68% | 18% |

A Fisher’s exact test of the data in Table 8 gives p<0.01, therefore, it is highly unlikely that client contributions and client benefit success are independent. The increase in success rate, relative to client benefits, from a project with and without a large degree of client involvement was as high as 52% (percentage points). Even more telling is that, similar to the findings in the original survey, none of the unsuccessful projects had a large degree of client contribution.

Table 9 shows, for the original survey, the increase in success rate for those responding with the category “Competent client” and “High client involvement” for the other success dimensions. The data suggests that client competence and involvement are positively connected with project success along most success dimensions. However, the increase in success rate is typically not very large, except for functionality and budget control, and for one success dimension (work efficiency) even negative for the higher competence of the client.

Table 9: Client competence (C1) and involvement (C2)

| Success dimensions | Competent client (C1) | High client involvement (C2) |
| --- | --- | --- |
| Functionality (n=58) | 23% | 14% |
| Technical quality (n=58) | 0% | 8% |
| Budget control (n=58) | 26% | 12% |
| Delivery on time (n=55) | 9% | 13% |
| Work efficiency (n=54) | -3% | 5% |

In total, the results suggest that a competent and involved client do play an important role for the success of software projects, and even more to avoid failures. It does, however, also suggest that to ensure successful client benefits, it is not the competence and involvement alone, but rather its use of in setting priorities and making timely decisions that matter. Implicitly, this also exemplifies that many software projects in our survey with competent and involved clients were not successful in delivering client benefits. As much as 62% of the projects in which the response was that the client was both competent and involved (n=21) were not successful with respect to delivering client benefits.

While a competent and involved client is likely to be important, we do not know very much about how a client should contribute and what skills, in which contexts, that are needed to enable successful software development projects. In other words, we do currently not know exactly what we mean by a competent and involved client and there is a need for more studies, providing more concrete results and advice on types of client competences and involvements essential for project success.

## 4.5 Contract type

Our hypothesis was that projects with fixed-price contracts would have less client benefit success (H3). To test this hypothesis and to explore the relation between contract type and the other success dimensions, we asked the survey participants to describe their contract model. We categorized their contracts as either per hour or fixed price. Most contracts were easily described as either of these types. Those including elements of both fixed-price and per-hour contracts (n=7) were categorized as fixed price given that a major part of the project deliveries were based on fixed price, otherwise as per-hour based. Nine projects had contracts based on risk sharing and target price. These contracts had mechanisms for sharing the “profit” if less effort was spent than targeted and sharing the “loss” if more effort than the targeted effort was spent. This type of risk-sharing contract was categorized as a fixed-price contract, since the profit sharing is relative to a “target price” which to some extent resembles a fixed-price. Some of these contracts may, however, have been closer to per-hour contracts based on how they shared the risk. Eight contracts used an agile type of contract, in which the price was to some extent fixed, but the deliveries were flexible to fit the agreed number of work-hours. This resembles a per-hour contract type, since all work-hours are paid for. We include a separate analysis of the risk sharing and agile contract types.

The proportion of fixed-price projects was 51%, a proportion similar to that found in other surveys [41-43]. There were slightly fewer large projects among those paid per hour (23% vs 37% large projects) and slightly higher client competence for per-hour contracts (59% vs 40% projects assessed to have a competent clients), but no other large differences in other project characteristics.

Table 10 displays the increase in project success for projects with per-hour compared with fixed-price contracts.

Table 10: Project success and contract type

| Success dimensions | Increase in success rate (percentage points) for projects applying per-hour rather than fixed-price contracts |
| --- | --- |
| Client benefit (n=49) | 34% |
| Functionality (n=51) | 5% |
| Technical quality (n=51) | 11% |
| Budget control (n=50) | 14% |
| Delivery on time (n=50) | 3% |
| Work efficiency (n=49) | 10% |

While there was a clear increase in success rate for client benefits when applying per-hour based contracts (p=0.02, supporting our hypothesis H3), there were only smaller differences for the other success dimensions. Consequently, it seems that there is a positive effect from using per-hour based contracts mainly for success related to client benefit.

A deeper look into the types of contracts used showed that projects with entirely per-hour contracts were the most successful with respect to client benefits (59% successes, n=17) and the entirely fixed-price contracts were the least successful (0% successes, n=8). Those using a combination of fixed-price and per-hour based contracts had a 29% success rate (n=7), those using risk sharing mechanisms a 22% success rate (n=7) and those using agile contracts a 29% (n=9) success rate on client benefits. One fixed-price project was not categorized into subgroup contract type, due to lack of information.

The analysis suggests that the closer a contract is to being billed entirely per-hour, the more likely it is to see success in relation to client benefits. Whether a fixed-price contract causes, or is mainly a symptom of, higher risk in not succeeding in delivering client benefits is hard to determine from the data. Projects using fixed-price contracts were similar to the other projects with respect to most characteristics, except that they had a stronger focus on low price when selecting providers, used fewer agile practices, and were less likely to include benefit management plans and benefit management practices during project execution. Consequently, it is possible that it is not the fixed-price contract itself that caused the lower proportion of successes, but rather the related tendency to focus on low price and less on competence when selecting providers, the reduced focus on benefit management practices, and the lower use of agile practices. The decision to use fixed-price projects may enforce a stronger focus on low price, see [57], and complicate the use of benefit management and agile processes during project execution, for example, through more complex processes for changing the scope to reflect changes in needs and learning.

## 4.6 Agile software development

We included questions about the presence of selected agile-related development process elements to assess their connection to project success. The included elements were as follows:

- P1: Agile development method

- P2: Frequent delivery to client

- P3: Scope flexibility

- P4: Prototyping

- P5: Automated testing

The questions were formulated as yes/no questions, that is, the respondents were instructed to state whether the project followed an agile development method, had frequent delivery to client, whether there was flexibility in scope to reflect changes in needs and learning, included prototyping, and/or included automated testing.

The analysis of the increase in success rate (in percentage points) comparing the situation with and without the specified process element is displayed in Table 11. For each column we compare the projects that were confirmed to use the agile element and those that were not.

Table 11: Increased rate of project success when agile element was present

| Success dimensions | Agile method | Frequent delivery | Scope flexibility | Prototyping | Automated testing |
| --- | --- | --- | --- | --- | --- |
| Client benefit (n=56) | 16% | 22% | 29% | 15% | 14% |
| Functionality (n=58) | 22% | 29% | 16% | 0% | 7% |
| Technical quality (n=58) | 21% | 6% | 32% | 28% | 16% |
| Budget control (n=58) | 2% | 22% | 29% | 15% | 27% |
| Delivery on time (n=55) | 8% | 11% | 24% | -16% | 15% |
| Work efficiency (n=54) | 11% | 5% | 24% | 7% | 13% |

All process elements, except the effect of prototyping on timely delivery, were connected with increased success rate for all success dimensions. The elements of scope flexibility and frequent delivery were connected with the strongest increase in client benefit success rate. These elements are usually, but not always, part of projects using agile methods. Interestingly, when projects claimed to be based on an agile method, but did not have a flexible scope, the success rate on client benefits was as low as 25% - lower than the average success rate of the projects. In comparison, the agile projects with flexible scope had a success rate of 42%. Similarly, when projects claimed to follow an agile method, but did not have frequent delivery to the client, the success rate on client benefits was as low as 22%, again lower than the total average. In comparison, the agile project with frequent delivery to the client had a success rate of 45%. This suggests that some agile elements are much more essential for the success of agile projects than others.

# 5. Discussion

The survey provides results on that which separates more and less successful software projects and provides implications for actions that may increase the likelihood of project success. The focus of the survey is on the delivered client benefits. Delivering client benefits is in many ways the main purpose of software projects and it is, we argue, debatable to analyze project success without including this success dimension. A focus on client benefits as a success criterion is particularly important since we found the other dimensions - especially the much more frequently reported success dimensions “being on time” and “being on budget” – to be only weakly correlated to success in delivering client benefits. The traditional success factor “having the specified functionality” may even be in conflict with success in delivering client benefits. That is, we found that changing the scope in accordance with changing business needs and learning (having a flexible scope rather than delivering the initially specified functionality) was a strong indicator of success in delivering client benefits. As far as we know, our study is the first study on the correlation between success dimensions in a software development project context. In comparison with projects from other domains, we found a stronger correlation between client benefits and success in meeting the functional or technical requirements, and a weaker correlation between client benefits and budget control, than those reported for non-IT projects in [58, 59]. Differences in domain and development processes may explain these differences.

Contrary to that which is commonly reported [34], usually with a focus on cost and time overruns, we did not find the proportion of successful projects to decrease with increased project size, as measured by the size of the project budget. However, when looking at the projects that failed to provide much client benefits, we see that the largest projects (those with a budget of more than 10 million euros) were strongly over-represented. A follow-up survey showed that the large projects were three to four times more likely to fail. Our results, therefore, support the advice of avoiding very large software projects by reducing scope or splitting larger projects into smaller ones, due to the higher failure rate of very large projects [4].

Our results support the previously found positive effect of the use of benefit management practices [35-37, 60], and extend previous results by identifying the key elements of benefit management. In particular we found that the existence of a benefit management plan and practices that enable prioritization of functionality and management of benefits during project execution were connected with significantly (p<0.05) higher client benefit success rates. The relations between benefit management practices and other success dimensions were weaker.

Contrary to the results from other studies [18, 61, 62], but corresponding with for example the results reported in [11], we did not find a strong connection between project success and client competence and involvement in the main survey. However, in the follow-up survey we learned that this may have been a consequence of the way in which we asked and the fact that we did not include cancelled project in the data set. When asking more directly about the contributions of the client in prioritizing requirements and taking decisions related to benefit management (that is, not only asking about whether the clients were competent and spent much effort on the project) we found clear connections between client contributions and project success. In addition, both the original survey and the follow-up survey found that all failed software projects were with less competent and less contributing clients. Our results, therefore, correspond with other studies emphasizing the importance of a competent and involved client, but also emphasizing that the competence and involvement have to translate into useful contributions to generate success.

There are mixed previous results on the effect of fixed-price and per-hour contracts on the success of software projects. In [63] the use of fixed-price contracts was described as a reason for project failures, while in [64] it was reported that the delivered quality was higher in fixed-price than in per-hour contracted Indian software projects. The majority of studies, as far as we are aware, seem to find that the use of fixed-price contracts increases the risk of unsuccessful projects [63, 65], and is connected with less trust between the provider and the client [43]. Our results are consistent with the majority of previous results, that is, suggesting a negative effect of fixed-price contracts on software project success. Especially for the success in delivering client benefits, project paid per hour had a much higher, statistically significant (p<0.05) success rate than the fixed-price projects. Some contract types were neither entirely fixed-price nor entirely per-hour payment. The closer the contracts were to being billed entirely per hour, the higher the likelihood of projects being successful in delivering client benefits. Fixed-price projects had stronger focus on low price when selecting providers and were less likely to use benefit management and agile practices, which may partly explain the lower success rate.

We found that the use of agile practices was connected with increased rates of success. The increase in success rate held for all analyzed success dimensions, not only client benefits. This supports previous studies on the benefits of agile practices, see for example [66]. We also found that some agile practices were more central to success than others and even that agile projects that did not include frequent delivery to the client or flexibility in scope had less than average success in delivering client benefits. There are only few previous studies on the relative importance of individual agile practices on project success. Our results correspond with those few that have been reported. The “delivery strategy” (including frequently delivery and flexibility of scope) was found to positively affect the success on meeting the requirements, time control and cost control in [11, 67]. No analysis on the effect of client benefits was reported in those studies.

# 6. Limitations

Our survey and analyses have limitations that should be considered when assessing the strength and generalizability of the results. We believe that the following are the most essential limitations and weaknesses:

- The results are based on relatively few observations of software projects. Among other things, this has the consequence that we have not included an analysis integrating all elements to find those which best explain project outcome, for example regression-model based analyses like those in [18].

- The included projects are not a random sample but a convenience sample based on Norwegian software clients and providers participating in a project management seminar. Consequently, the generalizability to other contexts is more difficult compared to including a representative or random sample from a larger population. Note that this is, to a larger degree, a problem when examining the actual success rates of the included software projects, but less so when examining how different factors are connected, as long as one can assume that the underlying success mechanisms are similar in different software development contexts.

- The high number of analyses and the degree of unexplained (stochastic) variations in outcome means that many of the connections may be there by chance. The high number of analyses caused us to formulate just a few (three) hypotheses in advance and use the remaining analyses as more exploratory work to pose hypotheses about characteristics of successful projects.

- The respondents knew the project outcome when they responded about the project characteristics. Knowing that a project has been unsuccessful may, for example, have biased the responses to be overly negative about the degree of client competence or the lack of benefit management processes. We were aware of this risk when designing the survey and consequently tried to request mainly objective information about the project characteristics. There is still the possibility that the respondents would have answered differently if the project outcome were unknown.

- A few seminar participants were from the same organizations and may potentially have reported information about the same project. It is also possible that individuals from both the providers and the clients reported on the same project, although from different perspectives. The size of the overlap in projects reported is hard to assess, given the anonymity of the respondents and projects. An analysis of the list of seminar participants shows that the overlap in projects is likely to be small. All those representing the same organization (a maximum of seven organizations) were from very large organizations, with many departments and many projects running in parallel. The number of recently completed projects of the provider and client companies represented at the seminar is very high and the inclusion of more than a few projects from the clients and the providers is, we believe, highly unlikely.

The results should be interpreted carefully and in the light of other evidence. When there is correspondence between the findings in this survey and those of surveys in different contexts and with different limitations, there are good reasons to think that the result is robust. When, however, the results diverge, as with the effect of fixed-price contracts in India and Norway, the results may be more context-dependent and/or less robust.

# 7. Conclusion

Summarizing the results, we see that, according to our survey results, a successful (or a non-failed) project tend to not bee very large (not larger than 10 million euros), use a per-hour contract, and have a client who is not only competent and spends many hours on the project, but also contributes with prioritizing requirements, making decisions and focusing on business benefits. In addition, a successful project tends to include a benefit management plan and mechanisms to implement the plan during project execution. Finally, it tends to use the agile practices of frequent deliveries to the client and flexibility in scope that enables meeting changes in needs and learning during the project. To increase the likelihood of successful software projects, as many of the above elements as possible should be included. For each element not in place, the risk of failing to deliver the expected client benefits may increase.

Funding: This work was supported by the Regional Research Funds of Norway.

References:

[1]	Goldfinch, S., Pessimism, computer failure, and information systems development in the public sector. Public Administration Review, 2007. 67(5): p. 917-929.

[2]	Bharadwaj, A., M. Keil, and M. Mähring, Effects of information technology failures on the market value of firms. The Journal of Strategic Information Systems, 2009. 18(2): p. 66-79.

[3]	Conboy, K., Project failure en masse: a study of loose budgetary control in ISD projects. European Journal of Information Systems, 2010. 19(3): p. 273-287.

[4]	Sauer, C., A. Gemino, and B.H. Reich, The impact of size and volatility on IT project performance. Communications of the ACM, 2007. 50(11): p. 79-84.

[5]	Tichy, L. and T. Bascom, The business end of IT project failure. Mortgage Banking, 2008. 68(6): p. 28.

[6]	El Emam, K. and A.G. Koru, A replicated survey of IT software project failures. IEEE Software, 2008. 25(5): p. 84-90.

[7]	Kappelman, L.A., R. McKeeman, and L. Zhang, Early Warning Signs of it Project Failure: The Dominant Dozen. Information Systems Management, 2006. 23(4): p. 31 - 36.

[8]	Yeo, K.T., Critical failure factors in information system projects. International Journal of Project Management, 2002. 20(3): p. 241-246.

[9]	Schmidt, R., et al., Identifying software project risks: An international delphi study. Journal of Management Information Systems, 2001. 17(4): p. 5-36.

[10]	Cole, A., Runaway projects: Cause and effects. Software World, 1995. 26(3): p. 3-5.

[11]	Chow, T. and D.-B. Cao, A survey study of critical success factors in agile software projects. Journal of Systems and Software, 2008. 81(6): p. 961-971.

[12]	McLeod, L. and S.G. MacDonell, Factors that affect software systems development project outcomes: A survey of research. ACM Computing Surveys (CSUR), 2011. 43(4): p. 24.

[13]	Nelson, R.R., IT project management: Infamous failures, classic mistakes and best practices. MIS Quarterly Executive, 2007. 6(2): p. 67-78.

[14]	Gotterer, M.H. Management of computer programmers. in Proceedings of the May 14-16, 1969, spring joint computer conference. 1969. ACM.

[15]	Bloch, M., S. Blumberg, and J. Laartz, Delivering large-scale IT projects on time, on budget, and on value. McKinsey Quarterly, 2012(October): p. 1-6.

[16]	Kitchenham, B., et al., Large-scale software engineering questions-expert opinion or empirical evidence? Software, IET, 2007. 1(5): p. 161-171.

[17]	Dybå, T., B. Kitchenham, and M. Jørgensen, Evidence-based software engineering for practitioners. IEEE Software, 2005(Jan-Feb): p. 58-65.

[18]	Jørgensen, M., Failure factors of small software projects at a global outsourcing marketplace. Journal of Systems and Software, 2014. 92: p. 157-169.

[19]	Hashmi, M.T. and P. Stevrin, High IT Failure Rate: A Management Prospect. Blekinge Tekniska Hogskola Sektionen for Management, 2009.

[20]	Ahimbisibwe, A., R.Y. Cavana, and U. Daellenbach, A contingency fit model of critical success factors for software development projects: A comparison of agile and traditional plan-based methodologies. Journal of Enterprise Information Management, 2015. 28(1): p. 7-33.

[21]	Lehtinen, T.O., et al., Perceived causes of software project failures–An analysis of their relationships. Information and Software Technology, 2014. 56(6): p. 623-643.

[22]	Whitney, K.M. and C.B. Daniels, The root cause of failure in complex IT projects: complexity itself. Procedia Computer Science, 2013. 20: p. 325-330.

[23]	Hashim, R., M. Abbas, and M. Hashim. Critical success factors assessment in software projects. in Science and Information Conference (SAI), 2013. 2013. IEEE.

[24]	Nasir, M.H.N. and S. Sahibuddin, Critical success factors for software projects: A comparative study. Scientific research and essays, 2011. 6(10): p. 2174-2186.

[25]	Agarwal, N. and U. Rathod, Defining ‘success’ for software projects: An exploratory revelation. International journal of project management, 2006. 24(4): p. 358-370.

[26]	Procaccino, J.D., et al., Case study: factors for early prediction of software development success. Information and software technology, 2002. 44(1): p. 53-62.

[27]	Procaccino, J.D. and J.M. Verner, Software project managers and project success: An exploratory study. Journal of Systems and Software, 2006. 79(11): p. 1541-1551.

[28]	Gingnell, L., et al., Quantifying Success Factors for IT Projects—An Expert-Based Bayesian Model. Information systems management, 2014. 31(1): p. 21-36.

[29]	Shrnhur, A.J., O. Levy, and D. Dvir, Mapping the dimensions of project success. Project management journal, 1997. 28(2): p. 5-13.

[30]	Shenhar, A.J., et al., Project success: a multidimensional strategic concept. Long range planning, 2001. 34(6): p. 699-725.

[31]	Budzier, A., Theorizing Outliers, in University of Oxford. 2014, University of Oxford.

[32]	Kitchenham, B., et al., An empirical study of maintenance and development estimation accuracy. Journal of systems and software, 2002. 64(1): p. 57-77.

[33]	Hill, J., L. Thomas, and D. Allen, Experts' estimates of task durations in software development projects. International journal of project management, 2000. 18(1): p. 13-21.

[34]	Jørgensen, M., T. Halkjelsvik, and B. Kitchenham, How does project size affect cost estimation error? Statistical artifacts and methodological challenges. International Journal of Project Management., 2012. 30(7): p. 839-840.

[35]	Serra, C.E.M. and M. Kunc, Benefits Realisation Management and its influence on project success and on the execution of business strategies. International Journal of Project Management, 2015. 33(1): p. 53-66.

[36]	Peppard, J., J. Ward, and E. Daniel, Managing the realization of business benefits from IT investments. MIS Quarterly Executive, 2007. 6(1): p. 1-11.

[37]	Doherty, N.F., C. Ashurst, and J. Peppard, Factors affecting the successful realisation of benefits from systems development projects: findings from three case studies. Journal of Information Technology, 2012. 27(1): p. 1-16.

[38]	Lacity, M.C. and L.P. Willcocks, An empirical investigation of information technology sourcing practices: lessons from experience. MIS quarterly, 1998: p. 363-408.

[39]	Lacity, M.C., S.A. Khan, and L.P. Willcocks, A review of the IT outsourcing literature: Insights for practice. The Journal of Strategic Information Systems, 2009. 18(3): p. 130-146.

[40]	Han, H.-S., et al., Complementarity between client and vendor IT capabilities: An empirical investigation in IT outsourcing projects. Decision Support Systems, 2013. 55(3): p. 777-791.

[41]	Tiwana, A., Does technological modularity substitute for control? A study of alliance performance in software outsourcing. Strategic Management Journal, 2008. 29(7): p. 769-780.

[42]	Arora, A., et al., The Indian software services industry. Research policy, 2001. 30(8): p. 1267-1287.

[43]	Fink, L., Y. Lichtenstein, and S. Wyss, Ex post adaptations and hybrid contracts in software development services. Applied Economics, 2013. 45(32): p. 4533-4544.

[44]	Laanti, M., O. Salo, and P. Abrahamsson, Agile methods rapidly replacing traditional methods at Nokia: A survey of opinions on agile transformation. Information and Software Technology, 2011. 53(3): p. 276-290.

[45]	Doyle, M., et al., Agile software development in practice, in Agile Processes in Software Engineering and Extreme Programming. 2014, Springer. p. 32-45.

[46]	Dybå, T. and T. Dingsøyr, Empirical studies of agile software development: A systematic review. Information and software technology, 2008. 50(9): p. 833-859.

[47]	Cao, L. and B. Ramesh, Agile requirements engineering practices: An empirical study. Software, IEEE, 2008. 25(1): p. 60-67.

[48]	Ferreira, C. and J. Cohen. Agile systems development and stakeholder satisfaction: a South African empirical study. in Proceedings of the 2008 annual research conference of the South African Institute of Computer Scientists and Information Technologists on IT research in developing countries: riding the wave of technology. 2008. ACM.

[49]	Lindvall, M., et al., Empirical findings in agile methods, in Extreme Programming and Agile Methods—XP/Agile Universe 2002. 2002, Springer. p. 197-207.

[50]	Ika, L.A., Project success as a topic in project management journals. Project Management Journal, 2009. 40(4): p. 6-19.

[51]	Markus, M.L. and J.-Y. Mao, Participation in development and implementation-updating an old, tired concept for today's IS contexts. Journal of the Association for Information Systems, 2004. 5(11): p. 14.

[52]	Nelson, R.R. and K.J. Jansen, Mapping and managing momentum in IT projects. MIS Quarterly Executive, 2009. 8(3): p. 141-148.

[53]	Halkjelsvik, T. and M. Jørgensen, From origami to software development: A review of studies on judgment-based predictions of performance time. Psychological Bulletin, 2012. 138(2): p. 238-271.

[54]	Jørgensen, M. and K. Moløkken-Østvold, How large are software cost overruns? A review of the 1994 CHAOS report. Information and Software Technology, 2006. 48(4): p. 297-301.

[55]	Jørgensen, M., The influence of selection bias on effort overruns in software development projects. Information and Software Technology, 2013. 55(9): p. 1640-1650.

[56]	Moløkken-Østvold, K., et al. A survey on software estimation in the Norwegian industry. in 10th International Symposium on Software Metrics. 2004. Chicago, IL: IEEE Computer Society.

[57]	Jørgensen, M. A strong focus on low price when selecting software providers increases the likelihood of failure in software outsourcing projects. in Proceedings of the 17th International Conference on Evaluation and Assessment in Software Engineering. 2013. ACM.

[58]	Dvir, D., T. Raz, and A.J. Shenhar, An empirical analysis of the relationship between project planning and project success. International Journal of Project Management, 2003. 21(2): p. 89-95.

[59]	Papke-Shields, K.E., C. Beise, and J. Quan, Do project managers practice what they preach, and does it matter to project success? International Journal of Project Management, 2010. 28(7): p. 650-662.

[60]	Coombs, C.R., N.F. Doherty, and I. Neaga, Measuring and Managing the Benefits from IT Projects: A Review and Research Agenda, in Transforming Field and Service Operations. 2013, Springer. p. 257-269.

[61]	Jun, L., W. Qiuzhen, and M. Qingguo, The effects of project uncertainty and risk management on IS development project performance: A vendor perspective. International Journal of Project Management, 2011. 29(7): p. 923-933.

[62]	Moløkken-Østvold, K. and K.M. Furulund. The relationship between customer collaboration and software project overruns. in Agile Conference (AGILE), 2007. 2007. IEEE.

[63]	Fabriek, M., et al. Reasons for Success and Failure in Offshore Software Development Projects. in ECIS. 2008.

[64]	Gopal, A. and B.R. Koka, The role of contracts on quality and returns to quality in offshore software development outsourcing. Decision Sciences, 2010. 41(3): p. 491-516.

[65]	Aundhe, M.D. and S.K. Mathew, Risks in offshore IT outsourcing: A service provider perspective. European Management Journal, 2009. 27(6): p. 418-428.

[66]	Serrador, P. and J.K. Pinto, Does Agile work?—A quantitative analysis of agile project success. International Journal of Project Management, 2015.

[67]	França, A.C.C., F.Q. da Silva, and L.M. de Sousa Mariz. An empirical study on the relationship between the use of agile practices and the success of Scrum projects. in Proceedings of the 2010 ACM-IEEE International Symposium on Empirical Software Engineering and Measurement. 2010. ACM.

# Appendix 1: Questions and response categories for the original survey

<The questions are translated from Norwegian. All questions included the options “Other (please describe)” and “Don’t know”. These options are not included below. Responses using “Other (please describe)” were evaluated by us and included in an existing category if judged appropriate or not included in the analysis if outside the scope of the analysis or not possible to categorize.>

Welcome to this on-line survey on benefit management in IT-projects. Your responses are anonymous. Neither we nor other people will be able to identify who has responded what to which questions. We ask for information about the last IT-project with budget larger than about 100.000 NOK <Corresponds to about 10.000 Euro> you have been involved in – as client or as provider – and which is now completed. If you have not been involved in any IT-project the last 5 years, do not respond to this questionnaire. You will have the opportunity to answer don’t know on every question and give your comments to the questions at the end of the survey. There is no requirement that you should have information about all aspects of the project to start the survey.

On behalf of the IT-management Network of the Oslo-region

Prof. Magne Jørgensen

Question 1: Your role in the project (multiple answers possible)

- On the client side of the project

- On the provider side

- Project leader

- Developer

Question 2: Client from the public or private sector

- Public

- Private

Question 3: Type of project (multiple answers possible)

- Development of a new software application

- Extending an existing software application

- Adapting/introducing an off-the-shelf application

Question 4: Budget

- Less than 10 mill. NOK <less than 1 mill. Euro>

- Between 10 and 100 mill. NOK <between 1 and 10 mill. Euro>

- More than 100 mill. NOK <more than 10 mill. Euro>

Question 5: Motivation for project (multiple answers possible)

- Modernization

- Increasing work/service efficiency

- Introducing new services or products

- Required changes (e.g., induced by new regulation)

Question 6: How much to you agree on the following statements related to benefit management in the project? (Scale: Fully agree – Agree more than disagree – Disagree more than agree – Fully Disagree)

- A good cost-benefit analysis of different alternatives was completed before the project started

- The expected benefits were clearly communicated to and understood by the project stakeholders

- There were good plans for how and when to realize the expected benefits

- There were good processes for prioritizing and managing activities during the project with focus on achieving the expected benefits

- There were good processes for evaluating (quantifying or formally assessing) the achieved benefits after the project was completed

Question 7: How much IT-competence had the client?

- Very much

- Much

- Some

- Little

- Very little

Question 8: What was the proportion of the total project effort completed by the client’s own staff?

- More than 40%

- Between 20 and 40%

- Less than 20%

- Almost nothing or nothing

Question 9: What was the contract type used for the project? (multiple answers possible)

- Fixed price

- Risk sharing-based contract

- Agile contract

- Per hour (time and material)

- Combination of contracts (please describe)

Question 10: How important was a low price when selecting provider?

- Very important (more than 50% weight)

- Important (30-50% weight)

- Less important (10-30% weight)

- Not important at all (less than 10% weight)

Question 11: Which of the following agile elements were present? (multiple answers possible)

- Agile development method (yes/no)

- Frequent delivery to client (yes/no)

- Scope flexibility (yes/no)

- Prototyping (yes/no)

- Automated testing (yes/no)

Question 12: How successful was the project with respect to the following dimensions? (Scale: Successful – Acceptable – Not very successful – Not at all successful)

- Client benefit (as compared with the expected benefits for the client)

- Functionality (as compared with the planned functionality)

- Technical quality of the deliveries

- Budget control

- Delivery on time

- Work efficiency

# Appendix 2: Questions and response categories for the follow-up survey

<Questions translated from Norwegian. All questions included the options “Other (please describe)” and “Don’t know”. These options are not included below. Responses using “Other (please describe)” were evaluated by us and included in an existing category if judged appropriate or not included in the analysis if outside the scope of the analysis or not possible to categorize. Notice that this survey, as opposed to the original survey, includes cancelled projects.>

Welcome to this brief on-line survey on management of IT-projects. Your responses are anonymous. Neither we nor other people will be able to identify who has responded what to which question. We ask for information about the two last IT-projects you have been involved in as client or provider, and which are either completed or cancelled in 2010-2014.  You should have relatively good knowledge about the project to complete the survey.

On behalf of the IT-management Network of the Oslo-region

Prof. Magne Jørgensen

Question 1: Your role in the project (multiple answers possible)

- On the client side of the project

- On the provider side of the project

Question 2: Budget

- Less than 10 mill. NOK <less than 1 mill. Euro>

- Between 10 and 100 mill. NOK <between 1-10 mill. Euro>

- More than 100 mill. NOK <more than 10 mill. Euro>

Question 3: To what degree had the project a client able to prioritize requirements, take decisions and focus on business benefits.

- To a large degree

- To some degree

- Ta small/no degree

Question 4: What was the outcome of the project with respect to client benefits?

- Successful

- Acceptable

- Not very successful

- Unsuccessful or cancelled